## Slide 1
Big Table Group
Project Kick Off

## Slide 2
Contents
Project Plan – Overview and Detail
Our Delivery Process
Azuronaut Project Team
Roles and Responsibilities
What we need from Big Table Group
  Access, Documents, Information
  Resource Requirement

## Slide 3
W/C 26/04 | W/C 03/05 | W/C 10/05 | W/C 17/05 | W/C 24/05 | W/C 31/05 | W/C 07/06 | W/C 14/06 | W/C 21/06 | W/C 28/06 | W/C 05/07 | W/C 12/07 | W/C19/07 |  |  |  |  |  | 
TECHNICAL SETUP
UAT TESTING
SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4 QA/TESTING
GO-LIVE
GO/NO-GO
GATEWAY
UAT GO/NO-GO
GATEWAY
Delivery Plan
END W/C 28/06
W/C 19/07

## Slide 4
Detailed Project Plan
Smartsheet link

## Slide 5
Our Delivery Process
Discover | Design | Develop | Deploy | Support
Requirements gathering User research Use cases Wireframe prototype User testing Delivery planning Formal proposal/SoW | Solution architecture Hi-fidelity design (HFD) User testing Completed user stories and backlog Release schedule | Development kick-off Development through planned sprints Test cases complete Quality checks Content creation/migration | Deployment UAT testing Handover documentation End-user training | Support and maintenance Training and usage support Microsoft technology support
GATEWAYS |  |  |  | 
Acceptance of proposal – agreement to proceed (Client) | Signed-off HFD and architecture | Signed-off development | Final sign-off | 
DELIVERABLES |  |  |  | 
Formal proposal/SoW Project plan Wireframe prototype Detailed requirements | Design system Delivery plan User stories and backlog Release schedule | Developed solution Documented development Weekly reports Change requests | Deployment of solution Completed test scripts Acceptance certificate issued | SLAs Ticketing and Issue Management
MEETINGS |  |  |  | 
Project kick-off meeting Project on-boarding Client workshops/meetings | Client workshops Planning meetings Sprint estimations Backlog prioritisation Client workshops/meetings | Kick-off meeting Daily stand-ups Sprint demos/retrospectives Design reviews | Client update meeting Client handover meeting Client go/no-go meeting | Client meeting Support sessions

## Slide 6
Digital Workspace Discovery/Development/Deployment
  Brett Sedcole – Head of Design and Delivery
  Adam Hunter – Project Manager
  Adeyemi Adelakun – Lead SharePoint Developer
  Brahma Kumar – Senior SharePoint Developer
  Alastair Roome – Senior Front-end Developer
Escalation
  Regan Collins – CEO
Azuronaut Project Team

## Slide 7
Azuronaut Project Team
Adam Hunter
Adam is a Microsoft 365 Project Manager delivering quality solutions utilising Microsoft 365 technology, with focus on Microsoft SharePoint. He is the key client contact during project delivery.
Project Manager
Microsoft 365 Certified – Fundamentals
Microsoft 365 Certified – Teams Administrator
Microsoft 365 Certified – Enterprise Administrator
Brett Sedcole
A design leader that is passionate about crafting meaningful, intuitive experiences that connect and empower people. Providing creative direction and growing capability to deliver leading-edge human centred design and world class digital experiences to organisations across the globe.
Head of Design and Delivery
Gold Award – Digital Experience Awards Best Website
Finalist – Innovative Enterprise Product of the Year
Finalist – Young Digital Professional of the Year
Finalist – Best Digital Team

## Slide 8
Azuronaut Project Team
Adeyemi Adelakun
Adeyemi is a Microsoft Certified Professional with over 18 years Microsoft experience. He has a wealth of technical and business skills acquired across a wide range of leading international commercial organisations.
Lead SharePoint Developer
Alastair Roome
With over 12 years of experience working with, and developing SharePoint. Al is involved in the Discovery right through to Deployment, developing high quality front-end interfaces for our solutions.
Lead Front-End Developer
Brahma Kumar
A Microsoft Certified Solutions Associate with over 14 years of extensive experience in Analysis, Design, Development, Testing, Implementation, Support of enterprise applications.
Senior SharePoint Developer

## Slide 9
Roles and Responsibilities
Product Owner
Delivers initial high-level requirements
Receives and approves proposals
Facilitates access to business stakeholders
Confirms and validates all requirements
Facilitates access to business stakeholders
Signs off hi-fidelity designs
Facilitates access to the relevant environments and software
Organises UAT testers
Signs off deliverables
Leads formal project close
Sarah Pope – Project sponsor
Technical Lead
Adeyemi Adelakun
Product Manager
Gather and understand requirements
Develop user research, cases, journeys and personas
Develop proposals
Ensure all user experience requirements are understood
Work with client to understand changes or additional requirements
Ensure all activities are delivered on time and to budget
Ensure deliverables are of high quality
Ensure solution is intuitive and has the user at the forefront of design and development
Review UAT responses and client feedback
Brett Sedcole
Understand user requirements
Develop solution architecture
Understand and be aware of all requirements updates that have been communicated and agreed
Communicate and document how each feature should be technically developed
Agree and confirm time for each feature to be developed
Ensuring all development activities are delivered on time and to budget
Ensure solution matches Hi-Fidelity designs
Ensure solution is intuitive and has the user at the forefront of design and development
Ensure solution is tested end-to-end
Ensure the solution is deployed

## Slide 10
Roles and Responsibilities
Project Manager
Ensuring all activities are delivered in budget and on time
Agree and confirm time for each feature to be developed
Create and manage development sprints
Ensure solution is tested end-to-end
Obtain sign off to exit the build phase
Ensure UAT is successfully run
Complete client handover
Ensure project is signed off
Adam Hunter
Designer
Ensure all user experience requirements are understood
Create Hi-Fidelity Designs
Ensure all designs activities are delivered on time and to budget
Ensure any requirements updates have been captured, communicated and agreed
Work with client to understand product changes or future requirements
Ensure solution matches hi-fidelity designs
Ensure solution is intuitive and has the user at the forefront of design and development
Brett Sedcole
Developers
Understand who the client is and why they need the proposed solution
Understand and be aware of all requirements updates that have been communicated and agreed
Understand how each feature should be technically developed
Agree and confirm time for each feature to be developed
Ensure solution is intuitive and has the user at the forefront of design and development
Ensure solution is tested end-to-end
Brahma Kumar and Alastair Roome

## Slide 11
What we need from Big Table Group
Access to MS Teams and Workplace:
BTG email address for Azuronaut
Enable System Admin access to Workplace
Enable Teams Service Admin access
Access to SharePoint and Azure:
SharePoint Site Collection Admin access
Azure Admin access
Defined Contact Persons
Technical Contact (Azure, SharePoint)
Content Contact (Links, Page Based Content)
Agree Project Team Weekly Session
  Time/Date
Accounts for access:
Four accounts with access:
  Adeyemi and Brahma
    Azure Admin
    Workplace Admin
    SharePoint Site Collection Admin
    Teams Service Admin
  Alastair
    SharePoint Site Collection Admin
  Two General User Accounts for Testing
Access, Documents, Information